# Food and Agriculture organization of the United Nations

### **Work Programme**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Name:** | Ismail Belen | | | | | | | | | |
| **Job Title\*\*:** | | | Legal Expert | | | | | | | |
| **Division/Department:** | | | | | FAOSEC | | | | | |
| **Programme/Project Number:** | | | | | | GCP/TUR/055/GFF | | | | |
| **Duty Station:** | | | Ankara, Turkey | | | | | | | |
| **Expected Start Date of Assignment:** | | | | | | | 1 July 2017 | **Duration:** | | 15 work days on WAE basis until 31 December 2017 |
| **Reports to:** | | ***Name:*** | | Peter Pechacek | | | | **Title:** | SEC Forestry Officer | |
|  | |  | |  | | | |  |  | |

|  |  |
| --- | --- |
| Outputs | Completion Date |
| Refined Work Program | 3 July 2017 |
| * Reading the project text and other related documents. * Review of recent developments in the project * Interview with project officials | 7 July 2017 |
| * Examination and reporting of relevant national legislation. * Examination and reporting of relevant international regulations. * Preparing a questionnaire for interviewees. | 14 July 2017 |
| Interview with a total of 12 people, including five senior (retired and working), five technical staff and two field workers / peasants. | 21 July 2017 |
| Depending on these studies, preparation of (draft) "SLM Legislation - Gap Analysis Report", sharing of results with interviewees and project officials. | 26 July 2017 |
| * Preparing for a workshop where these report outputs will be discussed. * Completion of the workshop announcement and other necessary work and procedures. | 28 July 2017 |
| Validation Workshop | 24 August 2017 |
| Revised ‘SLM Legislation - Gap Analysis Report’  Updating the report taking into account the workshop outputs. | 25 August 2017 |
| Conduct Needs Assessment at decision-making level of relevant government institutions about (international) best SFM/SLM governance practices and deliver respective Report | 31 August 2017 |
| Terminal Consultancy Report covering all works achieved | 8 September 2017 |