# Food and Agriculture organization of the United Nations

### Work Programme

| Name: | Ismail Belen |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Job Title**: |  |  | Legal Expert |  |  |  |  |  |  |  |
| Division/Department: |  |  |  |  | FAOSEC |  |  |  |  |  |
| Programme/Project Number: |  |  |  |  |  | GCP/TUR/055/GFF |  |  |  |  |
| Duty Station: |  |  | Ankara, Turkey |  |  |  |  |  |  |  |
| Expected Start Date of Assignment: |  |  |  |  |  |  | 1 July 2017 | Duration: |  | 15 work days on WAE basis until 31 December 2017 |
| Reports to: |  | Name: |  | Peter Pechacek |  |  |  | Title: | SEC Forestry Officer |  |

| Outputs | Completion Date |
| --- | --- |
| - Refined Work Program | 3 July 2017 |
| - Reading the project text and other related documents. - Review of recent developments in the project - Interview with project officials | 7 July 2017 |
| - Examination and reporting of relevant national legislation. - Examination and reporting of relevant international regulations. - Preparing a questionnaire for interviewees. | 14 July 2017 |
| - Interview with a total of 12 people, including five senior (retired and working), five technical staff and two field workers / peasants. | 21 July 2017 |
| - Depending on these studies, preparation of (draft) "SLM Legislation - Gap Analysis Report", sharing of results with interviewees and project officials. | 26 July 2017 |
| - Preparing for a workshop where these report outputs will be discussed. - Completion of the workshop announcement and other necessary work and procedures. | 28 July 2017 |
| - Validation Workshop | 24 August 2017 |
| - Revised ‘SLM Legislation - Gap Analysis Report’ - Updating the report taking into account the workshop outputs. | 25 August 2017 |
| - Conduct Needs Assessment at decision-making level of relevant government institutions about (international) best SFM/SLM governance practices and deliver respective Report | 31 August 2017 |
| - Terminal Consultancy Report covering all works achieved | 8 September 2017 |