8. An Action Plan for the implementation of the National Forestry Program on Forest Conservation and Development in the Republic of Azerbaijan, I stage: 2020-2025
 
	№
	Activity
	Expected results
	Executive bodies
	Execution period (years)

	1
	2
	3
	4
	5

	8.1. Ensure environmental and protective functions of forests, sustainable management and efficient use of forest resources

	8.1.1. Ensure and increase the usefulness of forests by maintaining the environmental and protective functions in front

	8.1.1.1.
	Management and use of forest areas to get benefit by maintaining the environmental and protective functions, implementation of tree cutting and processing activities in only limited forest areas
	The protective and environmental functions of the forests will be strengthened, the tree cutting will be carried out only in limited forest areas.
	MENR

	2020-2025

	8.1.1.2.
	Conduct research to assess and expand the protective functions of the forests and ecosystem services, develop and support assessment studies and awareness programs
	For the purposes of this, relevant researches will be conducted, evaluation studies and awareness programs will be developed and supported.
	MENR
NGO
ANAS
MoA
	2020-2025

	8.1.2. Sustainable resource management on non-timber forest products and the contribution of good practice to food security and the growth of incomes of indigenous people, private sector and forestry financing


	8.1.2.1.
	For the purpose of promoting sustainable use and trade of non-timber forest products, carry out analyses and economic studies on their production, production capacities, and potentials, and use their results
	Analyzes and studies on the use of non-timber forest products, their production, production capacities, and potentials will be carried out, and their results will be used.
	MENR
Ministry of Economy LEP NGO
	2020-2025

	8.1.2.2.
	Improve the regulatory framework for the production, processing, and trade of non-wood forest products
	The regulatory framework for the production, processing, and trade of non-timber forest products will be improved
	MENR
Ministry of Economy MoA
ANAS
	2020-2023

	8.1.2.3.
	Organize training for forest staff and indigenous people, including the private sector, in order to promote environmentally, socially and economically sustainable use of non-wood forest products
	The environmentally, socially and economically sustainable use of non-wood forest products will be promoted.
	MENR
Ministry of Economy MoA
LEP
Private sector,
Municipalities

	2020-2025

	8.1.2.4.
	Encourage small-scale processing and manufacturing enterprises for non-wood forest products by the private sector or in the form of a family business 
	Small-scale processing and manufacturing enterprises for non-timber forest products by the private sector or in the form of family business will be encouraged and the employment of the rural population will be ensured.
	MENR
Ministry of Economy MoA
MoH
Private sector,
LEP 
	2020-2025

	
8.1.3. More efficient use of wood obtained from service and sanitation cutting, organizing plantations of fast-growing tree types, meeting the indigenous people's energy needs by implementing other planned activities as a result of local needs and capacity assessment


	8.1.3.1.
	Renewal technical normative and regulative base on the measures for improving the condition of forests and sanitation cutting on the basis of the forest resources assessment results
	Technical norms and regulative base on the measures for improving the condition of forests and sanitation cutting will be renewed.

	MENR
ANAS
Ministry of Justice


	2020-2023

	8.1.3.2.
	Increase wood supplies by forest care and sanitation cuttings as possible in the relevant forest areas
	Wood supplies by forest management and sanitation cuttings will be increased.
	MENR,
Ministry of Economy

	2020-2025

	8.1.3.3.
	Encourage the cultivation of fast-growing and other useful timber types by indigenous people through appropriate measures, including awareness, technical assistance, and other economic initiatives
	The cultivation of fast-growing and other useful timber species by indigenous people will be promoted through the envisaged initiatives.
	MENR
LEP
Municipalities
NGO
MoA

	2020-2025

	8.1.4. Leasing land and resources of the relevant forestry fund to individuals or legal entities for the purpose of rational and productive use, without prejudice to the sustainability of ecosystems.


	8.1.4.1.
	Clearance of lease after the initial consultation with the public (lessee) and the lessor, making relevant changes to the legislation
	The lease procedure after the initial consultation with the public (lessee) and the lessor, and by making relevant changes to the legislation, will be improved.
	MENR
Ministry of Economy 
Ministry of Justice

	2020-2025

	 
	8.1.5.  Evaluation of the people's increasing demand for recreation and the capacity of the forests to meet this demand, supporting the proper use of such places by people


	 
	8.1.5.1.
	Support recreation and ecological tourism development in forest fund areas on the basis of a renewal of relevant normative legal base 
	Recreation and ecological tourism development in forest fund areas will be supported on the basis of a renewal of relevant normative legal base 
	MENR
Ministry of Economy
STA
MoH
LEP
	2020-2025

	 
	8.1.5.2.
	Elaborate and use appropriate curricula to encourage the proper use of the recreational places in the forests and the evaluation of such places by peoples in accordance with other relevant regulations, including prevention of fire and pollution

	Appropriate curricula to encourage the proper use of the recreational places in the forests in accordance with other relevant regulations, including prevention of fire and pollution, will be elaborated and used.

	MENR
MES
Ministry of Education
STA
NGO
	2020-2025

	 
	8.1.5.3.
	Involve indigenous people (community) in the use of the recreational and touristic places in the forests and encourage them to generate income
	Indigenous people (community) will be encouraged to involve in the use of the recreational and touristic places in the forests and they will be encouraged to generate income 

	MENR
STA
LEP
Municipalities

	2020-2025

	 
	8.1.6.  Development and submission of a certification system for sustainable forest management with stakeholders, as well as with relevant international organizations

	 
	8.1.6.1.
	Develop a certification system together with the international organization with relevant experience

	A certification system together with the international organization with relevant experience will be developed and submitted.


	MENR
International organizations
LEP
NGO

	2020-2025

	 
	8.1.6.2.
	Develop a national regulatory framework for this type of certification system, establish appropriate institutional capacity for the application of this system in forestry enterprises
	A national regulatory framework for this type of certification system will be developed, appropriate institutional capacity for the application of this system in other forestry enterprises will be established.
	MENR
Ministry of Economy 

	2020-2025

	 
	8.2. Measures on protection of forest resources and biodiversity, reducing negative effects and adaptation to the climate change 

	 
	8.2.1. Measures to eliminate the harmful effects of the people on forest resources, particularly to prevent illegal cutting of forests and to eliminate pressures related to grazing, recreation, and tourism

	 
	8.2.1.1.
	Strengthen the role and activities of local authorities and law enforcement authorities, and the institutional capacity of forestry institutions
	The role and activities of local authorities and law enforcement agencies and the institutional capacity of forestry institutions will be strengthened.


	MENR
LEP
Local law enforcement agency,
Municipalities

	2020-2025

	 
	8.2.1.2.
	Improve the legal framework for access to forest fund lands and resources, sustainable use of them (e.g., the supply of wood for fuel, grazing of animals, people's rest, etc.) 


	The legal framework for access to forest lands and resources, sustainable use of them will be improved
	MENR
MoJ
Ministry of Economy MoA

	2020-2022

	 
	8.2.1.3.
	Strictly forbid recreation activities in specially protected natural areas.
	The specially protected natural areas will be protected.

	MENR
MES, MoJ
 
	2020-2022

	
	8.2.1.4
	Establish protection zones in the forests for the endangered ecosystems and species of particular value
	The sufficient amount of biodiversity zones  will be established.
	MENR
ANAS

	2020-2025

	 
	8.2.1.5.
	Take relevant measures to prevent the mass destruction of the forests in the territories of Nagorno Karabakh occupied by Armenia and surrounding regions within the international initiatives and projects
	Relevant measures will be taken to prevent the mass destruction of the forests in the territories of Nagorno Karabakh occupied by Armenia and surrounding regions within the international initiatives and projects.
	MENR
MFA
MoJ
Representative offices of international organizations in Azerbaijan

	2020-2022

	 
	8.2.1.6.
	Promote sustainable resource management planning as a result of the assessment of forest resources

	Sustainable resource management planning in terms of meeting the needs of indigenous people as a result of the assessment of forest resources will be promoted.
	MENR
MoA
SCPI

	2020-2022

	 
	8.2.1.7
	Encourage the import of timber and the use of wood substitutes by taking relevant measures
	The import of timber and the use of wood substitutes will be encouraged by taking relevant measures.
	MENR
Ministry of Economy SCC
NGO
	2020-2025

	 
	8.2.2. Development and implementation of relevant measures and projects protecting biodiversity in forests

	 
	8.2.2.1.
	Strengthen the research and assessment on forest biodiversity, expand zones for biodiversity conservation



	The research and assessment of forest biodiversity will be strengthened; zones for biodiversity conservation will be expanded.
	MENR
SCPI
MoJ  
ANAS
	2020-2025

	 
	8.2.2.2.
	Develop and support the projects aimed at raising public awareness on the importance of forest biodiversity conservation, especially  intended for the youth and children
	The projects aimed at raising public awareness on the importance of forest biodiversity conservation, especially intended for the youth and children will be developed and supported.
	MENR
Ministry of Education
LEP
NGO
Mass media
	2020-2025

	
	8.2.2.3.
	Identification of the endangered ecosystems and enhancement of the special protection regime
	Access to the forest areas of particular importance will be restricted.
	MENR
	2020-2025

	
	8.2.3. Promotion and improvement of the sustainable management of grasslands and cattle-breeding resources around or in the forests

	
	8.2.3.1.
	Develop economic incentives and macro-credit programs to change the cattle grazing methods (transition from half-nomad grazing to grazing in a cattle farm)
	The half-nomad grazing methods will be gradually changed.
	MENR
MF
Ministry of Economy
MoA
	2020-2025

	
	8.2.3.2.
	The public awareness of sustainable grazing and grassland use were increased.
	The public will be  informed well on sustainable grazing and grassland use.
	MENR
LEP
MoA
Municipalities
	2020-2025

	[bookmark: _Hlk18568093]
	8.2.4. Reducing the forest dependence by improving the living standards of the people through the revenue diversity programs


	
	8.2.4.1. 
	Development and implementation of loan and grant support and local development programs for the local communities
	The local communities will be supported.
	MENR, MF, Ministry of Economy, MoA, Municipalities
	2020-2025

	
	8.2.4.2. 
	Promotion of the involvement of the locals (community) in the use of the recreation and tourism areas in the forests and their access to the revenues
	The local communities have access to additional revenues.
	MENR, STA, LEP, Municipalities
	2020-2025

	
	[bookmark: _Hlk18568113]8.2.5. Support to and improvement of the efficient and economical use by the people living around the forests and of the use of alternative energy sources

	
	8.2.5.1. 
	Ensuring the usage of more efficient and less polluting heating system at rural houses and provide them with proper isolation.
	Usage of wood reduced at rural areas
	MENR, Ministry of Energy, NGO
	2020-2025

	
	8.2.5.2.
	Enhancement of the enlightenment activities on the efficient and economical use of energy resources
	The enlightenment activities on the efficient and economical use of energy resources will be enhanced.
	MENR, Ministry of Energy, Ministry of Education, ANAS, NGO
	2020-2025

	
	8.2.5.3.
	To develop and implement program for public awareness on the alternative energy sources.
	The public was aware of  the alternative energy sources.
	MENR, MoA, MoE MoH, LEP, NGO, 
	2020-2025

	
	8.2.5.4.
	Support to the access by the rural population to the use of alternative energy sources
	The access by the rural population to the use of alternative energy sources will be supported.
	MENR, Ministry of Energy, Ministry of Economy
	2020-2025

	 
	[bookmark: _Hlk18568131]8.2.6. Improve the status of forests through taking ecologically harmless preventive and responsive measures against harmful diseases and forest fires

	 
	8.2.6.1.
	Strengthen ecologically harmless preventive and responsive measures against harmful diseases
	Ecologically harmless preventive and responsive measures against harmful insects and diseases will be improved.
	MENR
MoA, MoH

	2020-2025

	 
	8.2.6.2.
	Strengthen preventive and responsive measures against forest fires, with particular focus on awareness-raising activities
	Preventive and responsive measures against forest fires, with particular focus on awareness-raising activities, will be strengthened.
	MENR
MES, Ministry of Education, LEP,
NGO 
	2020-2025

	
	8.2.6.3.
	Review of the legislation to avoid the fire accidents in the farms or individual owners bordering the forests
	The respective actions will be taken to avoid the expected fire accidents in the mentioned areas.
	MENR, MES, MoJ, Ministry of Education, NGO
	2020-2025

	
	8.2.6.4. 
	Arrangement of the use of modern electronic observation devices to reduce the external interventions to the forests and fight against the forest fires
	Installation of observation cameras in the areas sensitive against anthropogenic and natural impacts
	MENR
	2020-2025

	
	8.2.6.5.
	Develop and use public awareness and training programs in connection with the preventive actions and struggling against forest fires with special attention towards the target groups (through television, radio and media, brochures, etc)
	Public awareness programs were developed.
	MENR, MES, Ministry of Education
	2020-2025

	
	8.2.6.6.
	Establish and/or improve access routes to and fire exits from the forests and increase the number of emergency actions for preventing the forest fires.
	The sufficient amount of routes and fires exits was established.
	MENR, MES
	2020-2025

	
	8.2.6.7.
	Take preventive actions in the forest areas practical for recreation and tourism, including the recreation areas belonging to the Forest Fund.
	Preventive actions were developed in the forest areas practical for recreation and tourism.
	MENR, STA, MES
	2020-2025

	
	8.2.6.8.
	Develop organizational points and chemical fire extinguishers, modern fire tracking (camera and computer-based) and warning systems to prevent the forest fires and ignitions.
	Organizational points exist with the modern camera and computer systems to fight against the fire.
	MENR, MES, MF
	2020-2025

	[bookmark: _Hlk18568151]
	
8.2.7. Raising the knowledge, skills and institutional capacities for the adaptation of forest management to climate change

	
	8.2.7.1.
	Increasing knowledge and skills of forestry institutions and other related organizations on climate change adaptation through conducting scientific studies and sharing their results with relevant international institutions and programs
	Knowledge and skills forestry institutions and other related organizations on climate change adaptation will be increased through programs to conduct scientific studies and share their results with relevant international institutions.
	MENR, MoA, ANAS, International organizations, NGO
	2020-2025

	
	8.2.7.2.
	Develop action plans for an adaptation of forest to climate change
	Action plans for an adaptation of forest to climate change will be developed.
	MENR, MoA, MES, SCPI
	2020-2022

	
	8.2.7.3.
	Identify and monitor carbon storage volumes of the forests
	Carbon storage volumes of the forests will be identified and monitored.
	MENR
ANAS
International Organizations

	2020-2025

	
	8.2.7.4.
	Increase the carbon storage capacity by rehabilitating and improving existing forests, expanding forest areas and planting trees in useful lands
	The carbon storage capacity will be increased by rehabilitating and improving existing forests, expanding forest areas and planting trees in useful lands


	MENR
MoA
SCPI
AAWF OJSC
SAAAR
Azerbaijan Railways CJSC
LEP
Municipalities
	2020-2025

	[bookmark: _Hlk18568268] 
	8.3. Significant expansion of forest areas through strengthening the measures of forest restoration and forestation

	
	8.3.1. Rehabilitation of degraded forests on the forest fund lands, improvement of forests and expansion of forest lands through forestation in the useful open forest fund lands and in the new land plots allocated to the forestry fund


	 
	8.3.1.1.
	Regeneration based on surveys and targeted projects, rehabilitation of the degraded forests through restoration and cultivation methods and forestation in the open forestry fund lands

	Relevant regeneration, rehabilitation of the degraded forests through restoration and cultivation methods and forestation in the open forestry fund lands will be realized.

	MENR
MoA
LEP
NGO
Municipalities
	2020-2025

	 
	8.3.1.2.
	Layout forest parks in the new land plots allocated to the forestry fund
	Forest parks in the new land plots allocated to the forestry fund will be laid out.
	MENR
Ministry of Economy, SCPI
MoA, LEP,
Municipalities
	2020-2025

	 
	8.3.2. Significant expansion of forest area in Azerbaijan by planting trees in the new land plots allocated to the forestry fund and in lands outside the forestry fund

	 
	8.3.2.1.
	Identification and allocation of additional lands outside the forestry fund for the purpose of forestation within the framework of a state-supported forestation campaign and on the basis of results of land cadaster 
	The additional useful lands outside of the forestry fund will be identified and allocated for the purpose of forestation and on the basis of results of land cadaster. 
	MENR, SCPI,
SAAAR 
AR CJSC
AAWF OJSC
LEP
Municipalities
	2020-2025

	 
	8.3.2.2.
	Inform relevant government agencies, educational institutions, NGOs, local communities and other stakeholders of the framework of this campaign, encourage their involvement in forestation and tree-planting
	Relevant government agencies, educational institutions, NGOs, local communities and other stakeholders will be informed, they will be encouraged to involve in forestation and tree-planting

	MENR, Ministry of Education,
SAAAR
ARCJSC
AAWF OJSC, LEP,
Municipalities,
NGO, Mass media
	2020-2025

	
	8.3.2.3.
	Renew technical norms, standards, including financial mechanisms for the organization and regulation of forest restoration activities within the framework of cooperation with relevant government agencies and other stakeholders 
	Technical norms, standards, including financial mechanisms for the organization and regulation of forest restoration activities will be renewed.
	MENR
MoJ, MoA,
ANAS, NGO
	2020-2022

	
	8.3.2.4.
	Research the collection and sowing of forest seeds, the the places for growing saplings, develop norms and standards

	The collection and sowing of forest seeds, the growing saplings will be researched and norms and standards will be developed.
	MENR
MoA, ANAS
	2020-2023

	
	8.3.2.5.
	Establish multipurpose tree plantations in the useful and private land plots outside of the forestry fund by forestry enterprises, other interested state agencies, local executive and municipal authorities, private companies

	Multipurpose tree plantations in the useful and private land plots outside of the forestry fund will be established by forestry enterprises, other interested state agencies, local executives, municipal authorities and  private companies

	MENR
MoA, SCPI,
SAAAR
AR CJSC
AAWF OJSC
LEP
Municipalities
Private sector
	2020-2025

	 
	8.3.3. Establishing new and up-to-date places for saplings and seed production areas and facilities to meet the growing needs of forestation areas and tree plantations for high-quality planting and sprouting materials, and improving existing infrastructure in this area 
 

	 
	8.3.3.1.
	Establish new and up-to-date places for saplings, seed production areas, and facilities for obtaining high-quality planting and sprouting materials
	New and up-to-date places for saplings, seed production areas and facilities will be established with the purpose of obtaining high-quality planting and sprouting materials
	MENR
MoA
SCPI

	2020-2023

	 
	8.3.3.2.
	Reconstruction of sapling farms for planting high-quality saplings by closed root system technology meeting the modern requirements.
	An appropriate base will be provided for planting saplings with the closed root system.
	MENR
MoA
International organizations
	2020-2022

	
	8.3.3.3.
	Improvement of the capacity of the seed growing laboratory under the Ministry
	A seed growing laboratory will be reconstructed and upgraded to the modern level.
	MENR, International Organizations MoF
	2020-2025

	 
	[bookmark: _GoBack]8.4. Improvement and strengthening of forest legislation, institutional capacity and funding mechanism in the context of sustainable forest management

	 
	8.4.1. Improvement of forest legislation within the framework of advanced forest law and strengthening of a favorable legal framework for sustainable forest management

	 
	8.4.1.1.
	Make appropriate changes to the Forest Code, other  laws and regulatory and normative legal acts on forest management

	Appropriate changes will be made to the Forest Code, other laws and regulatory and normative legal acts on forest management.

	MENR
MoJ, SCPI,
MoA

	2020-2022

	 
	8.4.1.2.
	Improve legal documents (statute, regulations, etc.) regulating the activities of state bodies implementing forest policy and other relevant bodies
  
	Legal documents (statute, regulations, etc.) regulating the activities of state bodies implementing forest policy and other relevant bodies will be improved.

	MENR, MoJ, Ministry of Economy, MoA, SCPI,
AAWF OJSC,
SAAAR,
Azerbaijan Railways CJSC
	2020-2022

	
	8.4.2. Improvement and co-ordination of interrelation of forest policy with other national, regional and sectoral development policies

	 
	8.4.2.1.
	Establish the National Forest Coordinating (Consultation) Body (Council) with the participation of high-level representatives of relevant state agencies, including financial institutions, in order to coordinate the  activities of international organizations (donors) and national policies for the sectors affecting forest development
	The National Forest Coordinating (Consultation) Body (Council) will be established with the participation of high-level representatives of relevant state agencies. 
	MENR
MoJ, Ministry of Economy,
MoA, MES
MoH, MF
STA
NGO
Mass media

	2020-2021

	
	8.4.2.2.
	Analysis of the duties and responsibilities of the relevant ministries and other state bodies related to natural resource management, improvement of regulatory documents that define their activities
	Regulatory documents that define the activities of the relevant ministries and other state bodies related will be improved.
	MENR
MoA, Ministry of Education, MES,
SCPI, STA
AAWF OJSC
SAAAR
	2020-2022

	
	8.4.2.3.
	Support the development and implementation of joint projects on the protection and use of forests and other natural resources in forest areas
	The development and implementation of joint projects on the protection and use of forests and other natural resources in forest areas will be supported.
	MENR
MoA, Ministry of Education, MES,
SCPI, STA,
AAWF OJSC
SAAAR
	2020-2025

	 
	8.4.3. Increasing institutional capacity, supporting and strengthening the activities of state forest bodies responsible for forest management by introducing up-to-date technical equipment, developing international cooperation

	 
	8.4.3.1.
	Establish new technical and other service units (non-timber forest products, communication, public relations, and community relations, climate change, etc.) to provide professional experience and services required to achieve strategic goals, provide them with the necessary staff training
	New technical and other service units will be established in order to provide professional experience and services, they will be provided with necessary staff training.

	MENR
MoA
Ministry of Economy AAWF OJSC
SAAAR
Azerbaijan Railways CJSC

	2020-2025

	 
	8.4.3.2.
	Increase knowledge and skills of forestry workers, improve working conditions, provide forestry enterprises with modern equipment
	Knowledge and skills of forestry workers will be increased, working conditions will be improved, and forestry enterprises will be provided with modern equipment.
	MENR
International organizations

	2020-2025

	
	8.4.3.3.
	Develop international cooperation on the issues of forestry within bilateral and multilateral programs and projects, as well as international conventions, organizations, foundations and agencies

	
	International cooperation will be developed on the issues of forestry
	MENR
MFA, Ministry of Economy,
International organizations

	2020-2025

	 
	8.4.4. Improving and strengthening the forest sector financing mechanism, promoting the participation and contribution of other stakeholders in this area

	 
	8.4.4.1.
	Strengthen financing of the forest sector through the efficient utilization of state budget and extra-budget funds allocation and the increase in forest revenues
 
	Financing of the forest sector will be strengthened through the efficient use of financial resources and the increase in forest revenues.
	MENR
MF
Ministry of Economy MoA
AAWF OJSC
	2020-2025

	 
	8.4.4.2.
	Ensure efficient use of the financial resources allocated to national foundations and private sector as well as international forestry projects
	Efficient use of the financial resources allocated to national foundations and private sector as well as international forestry projects will be ensured.
	MENR
MF
International organizations
Private sector
	2020-2025

	
	8.4.4.3.
	Develop proposals on improving the management of the Fund for Protection and Reproduction of Forests and other funds operating within the competence of MENR
	Proposals will be prepared on improving the management of the Fund for Protection and Reproduction of Forests and other funds operating within the competence of MENR

	MENR
MF
MoJ

	2020-2022

	 
	8.4.5. Improving and strengthening forestry education and research for sustainable forest management

	 
	8.4.5.1.
	Provide forestry enterprises with specialized staff, modern equipment and facilities, strengthen the capacities of staff through increased support for research programs and projects
	Forestry enterprises will be provided with specialized staff, modern equipment and facilities, the capacities of staff will be strengthened.

	MENR
MoA
ANAS

	2020-2025

	
	8.4.5.2.
	Prepare and implement relevant research projects related to priority issues and problems of forestry, communicate their results and recommendations to scientific research institutes, forestry enterprises, and other stakeholders
 
	Relevant research projects will be prepared and implemented, their results and recommendations will be communicated to scientific research institutes, forestry enterprises, and other stakeholders 

	MENR
MoA
ANAS


	2020-2025

	
	8.4.5.3.
	Strengthen the potential and programs of the Forestry faculty of the Azerbaijan State Agrarian University, organize specialist training on forestry specialty in other relevant universities
	The potential and programs of the Forestry faculty of the Azerbaijan State Agrarian University will be strengthened, and specialist training on forestry specialty in other relevant universities will be organized.
	MENR
MoA
Ministry of Education
ANAS

	2020-2025

	
	8.4.5.4.
	Establish College of Forestry and Vocational School of Forestry provided with modern equipment, professional staff, and advanced training program
	College of Forestry and Vocational School of Forestry will be established.
	MENR
Ministry of Education

	2020-2025

	
	8.4.5.5.
	Improve the knowledge and skills of forestry workers and enhance their qualification skills through relevant courses, training, and learning
	The knowledge and skills of forestry workers will be improved and their qualification skills will be enhanced through relevant courses, training, and learning.


	MENR
Ministry of Education
ANAS

	2020-2025

	 
	
8.5. Implementation of multi-purpose (integrated) management plans for forest management with a view to sustainable forest management


	
	8.5.1. Regular monitoring and evaluating of forests on the basis of updated and reliable databases

	 
	8.5.1.1.
	Elaborate appropriate guidelines to increase institutional capacity for inventory, monitoring, and evaluation of forests with the support of international cooperation projects
	Appropriate guidelines will be elaborated in order to increase institutional capacity for inventory, monitoring, and evaluation of forests with the support of international cooperation projects.
	MENR
SCPI,
International organizations
	2020-2025

	 
	8.5.1.2.
	Renew the inventory and assessment of forests on the basis of modern methods and technologies, establish the forest information and monitoring system
	The inventory and assessment of forests will be renewed, and the forest information and monitoring system will be established.
	MENR
SCPI
ANAS, International organizations

	2020-2022

	
	8.5.1.3.
	Develop proposals for strengthening institutional capacity and improving the regulatory framework and technical norms (standards), promote legal and technical training for relevant professionals, involving local people and other stakeholders
	Proposals for strengthening institutional capacity and improving the regulatory framework and technical norms (standards) will be developed, legal and technical training for relevant professionals, involving local people and other stakeholders will be promoted.


	MENR
MoA
AAWF OJSC
NGO
	2020-2025

	
	8.5.1.4.
	Develop multifunctional management plans for forest fund lands and resources
	Multifunctional management plans for forest fund lands and resources will be developed.
	MENR
MoA
AAWF OJSC
International Organizations

	2020-2023

	
	8.5.1.5
	Identify, monitor, assess and report Sustainable Forest Management Criteria and  Indicators for Azerbaijan. Test them at local level..
	SFM C&I for Azerbaijan will be identified, monitored, assessed and reported. SFM C&I will be tested in a rayon.
	MENR
International organizations
NGO
	2020-2025

	
	8.5.2. Promotion of the sustainable use of forests and non-wood products

	
	8.5.2.1.
	Update and amendment of norms and regulations on cutting to improve the sanitary conditions of forests
	The norms and regulations on cutting to improve the sanitary conditions of forests will be updated and amended.
	MENR/FDS

	2020-2025

	
	8.5.2.2.
	Performance of the scientific and operative research projects on the non-wood forest products (types, volume, and quality, harvesting, marketing)
	The research projects on the non-wood forest products will be performed.
	MENR/ FDS
Forestry faculty, Other research institutes
	2020-2025

	
	8.5.2.3.
	Train the forestry specialists and local groups on the sustainable supply, storage, processing and sale of the non-wood forest products
	The forestry specialists and local groups will be trained on the non-wood forest products.
	MENR/ FDS
 NGOs
	2020-2025

	
	8.5.2.4.
	Foundation of small-sized supply and processing institutions for the non-wood forest products by the private sector or households
	Pilot projects will be implemented for the demonstration of the processing institutions for non-wood forest products
	MENR/ FDS
MoA
	2020-2025

	
	8.5.2.5.
	Improve the road network in the forestry with the special attention towards the possible impacts 
	The road network will be improved in the forestry.
	MENR/ FDS, other relevant government agencies

	2020-2025

	
		8.5.3. Increasing participation and contribution of relevant government agencies, local executive and municipal bodies, NGOs and other stakeholders in the protection, conservation, rational use and expansion of forests

	
	8.5.3.1.
	Participation of government bodies, municipalities, local communities, NGOs, the private sector and other stakeholders in the decision-making and enforcement of forest management, encouraging their rights and responsibilities in this field
	Government bodies, municipalities, local communities, NGOs, the private sector and other stakeholders will be able to participate in the decision-making and enforcement of forest management, their rights, and responsibilities in this field will be encouraged


	MENR
LEP
Municipalities
Private sector
NGO

	2020-2025

	
		8.5.4. Implementation of sustainable hunting on the basis of the forestry fund by increasing knowledge and awareness of hunting

	
	8.5.4.1.
	Establish an appropriate regulatory framework and institutional capacities, as well as appropriate assessment and planning of wildlife and hunting resources
	Appropriate regulatory framework and institutional capacities will be established, as well as appropriate assessment and planning of wildlife and hunting resources will be implemented.
	MENR
MoJ
NGO

	2020-2023

	
	8.5.4.2.
	Arrange appropriate training for responsible persons for sustainable hunting issues and hunters
	Appropriate training for responsible persons for sustainable hunting issues and hunters will be arranged.
	MENR
STA
NGO

	2020-2025

	
	8.6. Awareness raising on the benefits of forests and involving the people in the sustainable forest management

	
	8.6.1.1. Development of programs on the necessary communication and information skills connected with the importance of forests

	
	8.6.1.1.
	Develop educational programs on the necessary communication skills and the opportunities for raising awareness on the importance of forests in forestry institutions and related institutions

	To this end, educational programs on the necessary communication skills and the opportunities for raising awareness on the importance of forests in forestry institutions and related institutions will be developed.

	MENR
Ministry of Education
MoA
AAWF OJSC


	2020-2022

	
	8.6.1.2.
	Introduce measures to increase participation and contribution of relevant government agencies, local executive and municipal bodies, NGOs and other stakeholders in public awareness activities for the protection and development of forests, natural environment, and biodiversity, promote their projects and programs through supporting financial and institutional mechanisms and other activities
	Measures for the protection and development of forests, natural environment and biodiversity will be introduced, projects and programs through supporting financial and institutional mechanisms and other activities will be promoted.

	MENR
MoE, MoA, 
NGO

	2020-2025

	
	8.6.1.3.
	Pay special attention to inform young people and children through innovative and attractive educational programs
	Special attention will be paid to inform young people and children through innovative and attractive educational programs.
	MENR
MoE, MES
MoA, LEP
NGO

	2020-2025

	
	8.6.1.4.
	Develop and implement special propaganda and campaign programs to increase public awareness through mass media
 
	Special propaganda and campaign programs will be developed and implemented in order to increase public awareness through mass media

	MENR
ANAS
NGO

	2020-2025

	
	8.6.1.5.
	Organize public seminars and meetings on the forestry and environmental matters
	The public will be informed on the forestry and environmental matters
	MENR, Ministry of Education, LEP, NGOs
	2020-2025

	
	8.6.1.6.
	Implement the corresponding educational and awareness building activities on forestry, ecology and other environmental matters for schoolchildren
	Schoolchildren will be informed on forestry, ecology and other environmental matters.
	MENR/FDS, Ministry of Education, NGOs
	2020-2025


 
 	

















 
	Acronyms 

	MENR
	Ministry of Ecology and Natural Resources of the Republic of Azerbaijan

	MoE
	Ministry of Economy of the Republic of Azerbaijan

	MoJ
	Ministry of Justice of the Republic of Azerbaijan

	MoE
	Ministry of Education of the Republic of Azerbaijan

	MES
	Ministry of Emergency Situations of the Republic of Azerbaijan

	MF
	Ministry of Finance of the Republic of Azerbaijan
 

	MFA
	Ministry of Foreign Affairs of the Republic of Azerbaijan

	MoA
	Ministry of Agriculture of the Republic of Azerbaijan

	MTCHT
	Ministry of Transport, Communications and High Technologies of the Republic of Azerbaijan

	MoH
	Ministry of Health of the Republic of Azerbaijan

	MoC
	Ministry of Culture of the Republic of Azerbaijan

	STA
	State Tourism Agency of the Republic of Azerbaijan

	SCC
	State Customs Committee of the Republic of Azerbaijan

	SCPI
	State Committee on Property Issues of the Republic of Azerbaijan

	MoE
	Ministry of Energy of the Republic of Azerbaijan

	SOCAR
	State Oil Company of the Republic of Azerbaijan

	ANAS
	Azerbaijan National Academy of Sciences

	AAWF OJSC
	Azerbaijan Amelioration and Water Farm Open Joint Stock

	SAAAR
	State Agency of Azerbaijan Automobile Roads

	AR CJSC
	Azerbaijan Railways CJSC

	LEP
	Local executive powers

	NGO
	Non-governmental organizations

	MM
	Mass media


 
 
 


